## CHAMPS Action Plan Template (Sample)

After using the “Activity Planning Checklist” to identify the activities your school to become a CHAMPS school, use this Action Plan template to lay out the steps get there.

| ###### Activity: Create a School Wellness team |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ###### Action Steps | ###### Who | ###### Due Date | ###### Date Completed | ###### Resources Required | ###### Tracking Methods | ###### Notes |
| Identify individuals to invite | ###### Principal Jones | ###### Sept 1 | ###### Sept 1 | ###### n/a | ###### List of invitees | ###### Helps to ask others for input too |
| Invite perspective members | ###### Principal Jones | ###### Sept 14 | ###### Sept 10 | ###### n/a | ###### Emails sent | ###### n/a |
| ###### Have interest meeting | ###### Principal Jones | ###### Oct 3 | ###### Oct 3 | ###### Meeting space, agendas | ###### Sign-In sheet, agenda | ###### 8/3: Lots of interest in participating! Decided to hold another meeting |